## Burn down chart
Release Burndown
Sprints completed | Expected Story Points Remaining | Actual Story Points Remaining
0 | 168 | 168
1 |  | 115
2 |  | 79
3 |  | 0
4 | 0 | 0
Sprint 1 Burndown
Sprint Days Remaining | Ideal Tasks Remaining | Actual Tasks Remaining
20 | 53 | 53
19 |  | 53
18 |  | 53
17 |  | 53
16 |  | 53
15 |  | 25
14 |  | 25
13 |  | 25
12 |  | 21
11 |  | 21
10 |  | 20.5
9 |  | 20.5
8 |  | 20.5
7
6
5
4
3
2
1
0 | 0
ALSO DO A SPRINT 2 BURNDOWN AS WELL