## Sprint 1
Release Burndown
Sprints completed | Expected Story Points Remaining | Actual Story Points Remaining
0 | 21 | 21
1 |  | 15
2 |  | 14
3 |  | 7
4 | 0 | 0
Sprint 1 Burndown
Sprint Days Remaining | Ideal Tasks Remaining | Actual Tasks Remaining
20 | 25 | 25
19 |  | 25
18 |  | 25
17 |  | 25
16 |  | 25
15 |  | 25
14 |  | 24
13 |  | 20
12 |  | 18
11 |  | 17
10 |  | 15
9 |  | 13
8 |  | 11
7 |  | 9
6 |  | 5
5 |  | 5
4 |  | 4
3 |  | 3
2 |  | 3
1 |  | 3
0 | 0 | 3

## Sprint 2
Release 2 Burndown
Sprints completed | Expected Story Points Remaining | Actual Story Points Remaining
0 | 40 | 40
1 |  | 29
2 |  | 22
3 |  | 12
4 | 0 | 0
Sprint 2 Burndown
Sprint Days Remaining | Ideal Tasks Remaining | Actual Tasks Remaining
20 | 66 | 66
19 |  | 66
18 |  | 66
17 |  | 66
16 |  | 66
15 |  | 66
14 |  | 65
13 |  | 65
12 |  | 57
11 |  | 57
10 |  | 47
9 |  | 47
8 |  | 47
7 |  | 32
6 |  | 32
5 |  | 25
4 |  | 25
3 |  | 16
2 |  | 16
1 |  | 9
0 | 0 | 0