## Sprint 1
Release Burndown
Sprints completed | Expected Story Points Remaining | Actual Story Points Remaining
0 | 53 | 53
1 |  | 37
2 |  | 25
3 |  | 15
4 | 0 | 0
Sprint 1 Burndown
Sprint Days Remaining | Ideal Tasks Remaining | Actual Tasks Remaining
20 | 25 | 25
19 |  | 25
18 |  | 25
17 |  | 25
16 |  | 25
15 |  | 25
14 |  | 24
13 |  | 20
12 |  | 18
11 |  | 17
10 |  | 15
9 |  | 13
8 |  | 11
7 |  | 9
6 |  | 5
5 |  | 5
4 |  | 4
3 |  | 3
2 |  | 3
1 |  | 2
0 | 0 | 0

## Sprint 2
Release 2 Burndown
Sprints completed | Expected Story Points Remaining | Actual Story Points Remaining
0 | 36 | 36
1 |  | 29
2 |  | 22
3 |  | 12
4 | 0 | .
Sprint 2 Burndown
Sprint Days Remaining | Ideal Tasks Remaining | Actual Tasks Remaining
20 | 60 | 60
19 |  | 59
18 |  | 58
17 |  | 58
16 |  | 58
15 |  | 55
14 |  | 53
13 |  | 49
12 |  | 47
11 |  | 44
10 |  | 41
9 |  | 38
8 |  | 35
7 |  | 32
6 |  | 29
5 |  | 26
4 |  | 21
3 |  | 15
2 |  | 9
1 |  | 3
0 | 0 | 0