## Sprint 1
Release Burndown
Sprints completed | Expected Story Points Remaining | Actual Story Points Remaining
0 | 37 | 37
1 |  | 30
2 |  | 25
3 |  | 15
4 | 0 | 0
Sprint 1 Burndown
Sprint Days Remaining | Ideal Tasks Remaining | Actual Tasks Remaining
20 | 25 | 25
19 |  | 25
18 |  | 25
17 |  | 25
16 |  | 25
15 |  | 25
14 |  | 24
13 |  | 20
12 |  | 18
11 |  | 17
10 |  | 15
9 |  | 13
8 |  | 11
7 |  | 9
6 |  | 5
5 |  | 5
4 |  | 4
3 |  | 3
2 |  | 3
1 |  | 3
0 | 0 | 3

## Sprint 2
Release 2 Burndown
Sprints completed | Expected Story Points Remaining | Actual Story Points Remaining
0 | 36 | 36
1 |  | 29
2 |  | 22
3 |  | 12
4 | 0 | .
Sprint 2 Burndown
Sprint Days Remaining | Ideal Tasks Remaining | Actual Tasks Remaining
20 | 60 | 60
19 |  | 59
18 |  | 59
17 |  | 59
16 |  | 59
15 |  | 59
14 |  | 59
13 |  | 59
12 |  | 51
11 |  | 51
10 |  | 41
9 |  | 41
8 |  | 41
7 |  | 32
6 |  | 32
5 |  | 25
4 |  | 25
3 |  | 16
2 |  | 16
1 |  | 9
0 | 0 | 0