## Burn down chart
Release Burndown
Sprints completed | Expected Story Points Remaining | Actual Story Points Remaining
0 | 53 | 53
1 |  | 37
2 |  | 5
3 |  | 3
4 | 0 | 0
Sprint 1 Burndown
Sprint Days Remaining | Ideal Tasks Remaining | Actual Tasks Remaining
20 | 25 | 25
19 |  | 25
18 |  | 25
17 |  | 25
16 |  | 25
15 |  | 25
14 |  | 24
13 |  | 20
12 |  | 18
11 |  | 17
10 |  | 15
9 |  | 13
8 |  | 11
7 |  | 9
6 |  | 5
5 |  | 5
4 |  | 4
3 |  | 3
2 |  | 3
1 |  | 2
0 | 0 | 0
ALSO DO A SPRINT 2 BURNDOWN AS WELL